## Slide 1: Agile SCRUM Basics

## Slide 2
What is Scrum?
History of Scrum
Values
Meetings
Iterative & Incremental
Self-Organized
1986- Hirotaka & Ikujiro Introduced
1990- Ken Schwaber used Scrum
1995 – Sutherland & Schwaber
2001 – Schwaber & Mike Beedle -Agile Software Development with Scrum- Book released
2002- Scrum Alliance founded by Schwaber
2009 – Schwaber left from Scrum Alliance & founded Scrum.org
Commitment
Courage
Focus
Openness
Respect
Product Owner
Development Team
Scrum Master
Sprint Planning
Daily Scrum
Sprint Review
Sprint Retrospective
Backlog Refinement
Scrum of scrums
Agile Scrum Overview
Roles

## Slide 3
Project Life Cycle
Project Conception/
Initiation
Close Project
Planning
Execution
Monitoring & Control
Project Management Plan
Project Charter
Status & Tracking
Planned
Actuals
Planned
Actuals
Vs.
Risk
Resources

## Slide 5: Velocity – is the Key Metric in Scrum

## Slide 6: Burndown Chart

## Slide 7: Project management - Kanban
Kanban is a visual signal that's used to trigger an action
Notes: Kanban is a visual signal that's used to trigger an action. The word kanban is Japanese and roughly translated means “card you can see.” Toyota introduced and refined the use of kanban in a relay system to standardize the flow of parts in their just-in-time (JIT) production lines in the 1950s.

## Slide 8
Project Management - Methodologies

## Slide 9
PLAN DRIVEN
CHANGE DRIVEN

## Slide 10: The Agile Manifesto–a statement of values
Process and tools
Individuals and interactions
over
Following a plan
Responding to change
over
Source: www.agilemanifesto.org
Comprehensive documentation
Working software
over
Contract negotiation
Customer collaboration
over

## Slide 11: Putting it all together
Image available at www.mountaingoatsoftware.com/scrum

## Slide 12: Sequential vs. Overlapping development
Source: “The New New Product Development Game” by Takeuchi and Nonaka. Harvard Business Review, January 1986.
Rather than doing all of one thing at a time...
...Scrum teams do a little of everything all the time
Requirements
Design
Code
Test

## Slide 13: Scrum Framework
Product owner
ScrumMaster
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

## Slide 14: Scrum Framework
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts
Product owner
ScrumMaster
Team
Roles

## Slide 15: Product owner
Define the features of the product
Decide on release date and content
Be responsible for the profitability of the product (ROI)
Prioritize features according to market value
Adjust features and priority every iteration, as needed
Accept or reject work results

## Slide 16: The Scrum Master
Represents management to the project
Responsible for enacting Scrum values and practices
Removes impediments
Ensure that the team is fully functional and productive
Enable close cooperation across all roles and functions
Shield the team from external interferences

## Slide 17: The Team
Typically 5-9 people
Cross-functional:
  Programmers, testers, user experience designers, etc.
Members should be full-time
    May be exceptions (e.g., database administrator)

## Slide 18: The Team
Teams are self-organizing
  Ideally, no titles but rarely a possibility
Membership should change only between sprints

## Slide 19: Scrum Framework
Product owner
ScrumMaster
Team
Roles
Product backlog
Sprint backlog
Burndown charts
Artifacts
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies

## Slide 20
Sprint planning meeting
Sprint prioritization
Analyze and evaluate product backlog
Select sprint goal
Sprint planning
Decide how to achieve sprint goal (design)
Create sprint backlog (tasks) from product backlog items (user stories / features)
Estimate sprint backlog in hours
Sprint
goal
Sprint
backlog
Business conditions
Team capacity
Product backlog
Technology
Current product

## Slide 21: Sprint planning
Team selects items from the product backlog they can commit to completing
Sprint backlog is created
  Tasks are identified and each is estimated (1-16 hours)
  Collaboratively, not done alone by the ScrumMaster
High-level design is considered
As a vacation planner, I want to see photos of the hotels.
Code the middle tier (8 hours)
Code the user interface (4)
Write test fixtures (4)
Code the foo class (6)
Update performance tests (4)

## Slide 22: The Daily scrum
Parameters
  Daily
  15-minutes
  Stand-up
Not for problem solving
  Whole world is invited
  Only team members, ScrumMaster, product owner, can talk
Helps avoid other unnecessary meetings

## Slide 23: Everyone answers 3 questions
These are not status for the ScrumMaster
  They are commitments in front of peers
What did you do yesterday?
1
What will you do today?
2
Is anything in your way?
3

## Slide 24: The Sprint review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
  2-hour prep time rule
  No slides
Whole team participates
Invite the world

## Slide 25: Sprint Retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
  ScrumMaster
  Product owner
  Team
  Possibly customers and others

## Slide 26: Start / Stop / Continue
Whole team gathers and discusses what they’d like to:
Start doing
Stop doing
Continue doing
This is just one of many ways to do a sprint retrospective.

## Slide 27: Scrum framework
Product owner
ScrumMaster
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

## Slide 28: Product backlog
The requirements
A list of all desired work on the project
Ideally expressed such that each item has value to the users or customers of the product
Prioritized by the product owner
Reprioritized at the start of each sprint
This is the product backlog

## Slide 29: A Sample product backlog
Backlog item | Estimate
Allow a guest to make a reservation | 3
As a guest, I want to cancel a reservation. | 5
As a guest, I want to change the dates of a reservation. | 3
As a hotel employee, I can run RevPAR reports (revenue-per-available-room) | 8
Improve exception handling | 8
... | 30
... | 50

## Slide 30: The Sprint goal
A short statement of what the work will be focused on during the sprint
Database Application
Financial services
Life Sciences
Support features necessary for population genetics studies.
Support more technical indicators than company ABC with real-time, streaming data.
Make the application run on SQL Server in addition to Oracle.

## Slide 31: Managing the sprint backlog
Individuals sign up for work of their own choosing
  Work is never assigned
Estimated work remaining is updated daily

## Slide 32: Managing the sprint backlog
Any team member can add, delete or change the sprint backlog
Work for the sprint emerges
If work is unclear, define a sprint backlog item with a larger amount of time and break it down later
Update work remaining as more becomes known

## Slide 33: A sprint backlog
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Write the foo class
Mon
8
16
8
12
8
Tues
4
12
16
8
Wed
Thur
4
11
8
4
Fri
8
8
Add error logging
8
10
16
8
8

## Slide 34: A sprint burndown chart
Hours

## Slide 35
Hours
40
30
20
10
0
Mon
Tue
Wed
Thu
Fri
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Mon
8
16
8
12
Tues
Wed
Thur
Fri
4
12
16
7
11
8
10
16
8
50

## Slide 36: Scalability
Typical individual team is 7 ± 2 people
  Scalability comes from teams of teams
Factors in scaling
  Type of application
  Team size
  Team dispersion
  Project duration
Scrum has been used on multiple 500+ person projects

## Slide 37: Scaling through the Scrum of scrums

## Slide 38: Scrum of scrums of scrums

## Slide 39: SCRUM Meetings (2 weeks Sprint)
Sprint Planning Meeting- 4 – 8 Hours
Daily Scrum Meeting – 15 Minutes
  What I did yesterday?
  What I will today?
  Impediment
Sprint Review Meeting – 1 – 2 Hours. Live demo
Sprint Retrospective Meeting – 2 Hours
  Find the cause , not people
Backlog Refinement Meeting – 2 Hours

## Slide 40: SCRUM Artifacts
Product Backlog
  The product backlog comprises an ordered list of requirements that a Scrum Team maintains for a product.
Sprint Backlog
  The Sprint Backlog is the list of work the Development Team must address during the next Sprint.
Product Increment
  The increment (or potentially shippable increment, PSI) is the sum of all the Product Backlog Items completed during a Sprint, integrated with the work of all previous Sprints.
Sprint burn-down chart
  The Sprint burn-down chart is a public displayed chart showing remaining work in the Sprint Backlog. Updated every day, it gives a simple view of the Sprint progress.
Release burn-up chart
  The release burn-up chart is a way for the team to provide visibility and track progress toward a release. Updated at the end of each Sprint, it shows progress toward delivering a forecast scope.